Draft Timeline Culham Community Led Plan

February 2012– launch event.

March – Apr – set up steering group and set parameters, constitution & collect ideas

May – Plant sale survey

July – ORCC event on best practice for CLP

August 20th – steering group meet: decide on budget, agree timetable, organise volunteers for bbq; look at skill-set in village; mtg dates to change to 1st Tuesday in month

Aug 25th – charity bbq at Waggon & Horses (volunteers needed), photocopy map of Culham

Sept 4th – steering group meet: finalise timetable, organise volunteers for door-to –door; look at questions from other villages

Sept – print flyers as publicity; suggestion box in pub/ Mouthpiece regular slots begin

Sept – Harvest Festival event in village? And/or door-to-door visits

Oct 2nd – steering group meet: organise young people’s event/dates for photographic walks/Bonfire Night; software options for questionnaire

Nov 6th – steering group meet: results from event

Nov – young people’s event/ Bonfire Night – young people’s event (Nov 10th will be Fireworks on Rec)

Dec 4th– Steering group meet: Xmas event (with local groups, eg. LoC?)

Jan 2013 -  Drafting of questionnaire

Jan 8th (Note change of date) steering group meet : questionnaire discussion & drafting

Feb 5th - steering  group meet: questionnaire final for pilot

Feb  - pilot questionnaire with 5 people?

Mar 5th:  steering group meet to change questionnaire /finalise

Apr  – questionnaire printed & distributed.

May  - questionnaire collected

June – interim report of questionnaire at event/ open gardens, collect comments & priorities

Jul 15th steering group meet: agree final report/ prioritise actions

July/Aug – report amendments/finalised & sent to printer

Sept – Official launch of report – event.