## CCG Budget
Culham Community Group - Start Up Budget/Timeline
4th Sept 2012
| Income | Expenditure | Donated time | Comments
2012-02-01 | 0 |  | 2hrs | Launch event at Culham School
2012-03-01 | 0 |  | 2hrs | Set up steering group and set parameters
2012-04-01 | 0 |  | 2hrs | Collect ideas and agree constitution
2012-05-01 | 0 |  | 7hrs | Survey at the plant sale
2012-06-01 | 0 |  | 2hrs
2012-07-01 | 0 |  | 2hrs | ORCC event in Cassington on best practice for CLP
2012-08-01 | 0 | 100 | 7hrs | Survey at Waggon & Horses BBQ
2012-09-01 | 0 | 175 | 62 hrs | Finalise timetable, organise volunteers for door-to-door, look at questions from other villages. Print flyers as publicity, buy suggestion box for village. Banner for roadside. Start Mouthpiece regular slot. Harvest festival event in village. Start door-to-door?
2012-10-01 | 0 | 260 | 3 hrs | Organise young people's event, dates for photographic walk, Bonfire night, discuss options for questionnaire software, buy 2 x A-boards for display in village
2012-11-01 | 0 | 210 | 11 hrs | Review and collate results from events. Young people's event. Bonfire night (Nov 10th)
2012-12-01 | 0 | 160 | 3 hrs | Christmas event. Start Facebook ads on CCG page
2013-01-01 | ?? | 10 | 9 hrs | Grant from ORCC? Draft questionnaire
2013-02-01 | 0 | 10 | 5.5 hrs | Finalise pilot questionnaire and pilot with 5 people
2013-03-01 | 0 | 310 | 3 hrs | Finalise questionnaire. Purchase software for analysis.
2013-04-01 | 0 | 242 | 7 hrs | Print & distribute questionnaire
2013-05-01 | 0 | 60 | 11 hrs | Collect questionnaire. Raffle prize awarded.
2013-06-01 | 0 | 40 | 13 hrs | Analysis of questions; interim report of findings from questionnaire at an event/open gardens. Collect comments & priorities
2013-07-01 | 0 | 10 | 3 hrs | Steering group to agree final report and prioritise actions
2013-08-01 | 0 | 310 | 3 hrs | Final report amendments and send report to printer
2013-09-01 | 0 | 310 | 3 hrs | Official launch of report at a special event
2013-10-01 | 0 | 10 | 3 hrs
2013-11-01 | 0 | 10 | 3 hrs
2013-12-01 | 0 | 10 | 3 hrs
|  | 100 |  | Volunteers out of pocket expenses
|  | 45 |  | Travel expenses for relevant county events
Totals | 0 | 2382 | 1690
Note on C11: Stand for village events - £85 Print & laminate village map - £15
Note on C12: Suggestion box for CCG - £30 Publicity flyers - (160 x 50p) £80 Banner - £65
Note on C13: Meeting room hire £10 2 x A-boards @ £125 each - £250
Note on C14: Meeting room hire £10 Young people's event - £200
Note on C15: Meeting room hire £10 Facebook ads - £5 per day x 30 days - £150
Note on C16: Meeting room hire £10
Note on C17: Meeting room hire £10
Note on C18: Meeting room hire £10 Analysis software - £250 + vat
Note on C19: Meeting room hire £10 Print questionnaire 160 x £1.45 - £232
Note on C20: Meeting room hire £10 Raffle prize £50
Note on C21: Meeting room hire £10 Event expenses - £30
Note on C22: Meeting room hire £10
Note on C23: Meeting room hire £10 Printing of 160 final reports - £300
Note on C24: Meeting room hire £10 Event for launching the report £300
Note on C25: Meeting room hire £10
Note on C26: Meeting room hire £10
Note on C27: Meeting room hire £10
Note on D5: Monthly update of website inc minutes distribution - 2 hrs
Note on D6: Monthly update of website inc minutes distribution - 2 hrs
Note on D7: Monthly update of website inc minutes distribution - 2 hrs
Note on D8: Monthly update of website inc minutes distribution - 2 hrs Plant sale - 5 hrs
Note on D9: Monthly update of website inc minutes distribution - 2 hrs
Note on D10: Monthly update of website inc minutes distribution - 2 hrs
Note on D11: Monthly update of website inc minutes distribution - 2 hrs BBQ survey - 5 hrs
Note on D12: Door to door - 60 hrs (160 houses x 20 mins) Monthly update of website inc minutes distribution - 2 hrs
Note on D13: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D14: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs Young people's event - (4 x 2 hours) 8 hrs
Note on D15: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D16: Mouthpiece article - 1hr Draft questionnaire - 6 hrs Monthly update of website inc minutes distribution - 2 hrs
Note on D17: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs Pilot questionnaire (5 x 30 mins) 2.5 hrs
Note on D18: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D19: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs Distribute questionnaire 4 hrs
Note on D20: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs Collect questionnaire - 8 hrs
Note on D21: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D22: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D23: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D24: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D25: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D26: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs
Note on D27: Mouthpiece article - 1hr Monthly update of website inc minutes distribution - 2 hrs